## Shopenzer Testcases
|  |  |  | Date | 2022-11-03
|  |  |  | Team ID | PNT2022TMID15585
|  |  |  | Project Name | Project - Plasma Donor Application
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
LoginPage_TC_OO1 | Functional | Login page | Verify user is able to see the Login page |  | 1.Enter URL and click go. 2.Verify login page is displayed or not. | http://127.0.0.1:5000/ | Login page should display | Working as expected | Pass |  |  |  | Abbireddy Sai Jahnavi
LoginPage_TC_OO2 | UI | Login page | Verify the UI elements in Login page |  | 1.Enter URL and click go. 2.Verify login page with below UI elements: a.email text box b.password text box c.Submit button d.New user? Signup link | http://127.0.0.1:5000/ | Application should show below UI elements: a.email text box b.password text box c.Submit button d.New user? Signup | Working as expected | Pass |  |  |  | Anandhitha TR
LoginPage_TC_OO3 | Functional | Login page | Verify user is able to log into application with Valid credentials |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button | Username: testuser@gmail.com password: testuser-1 | User should navigate to user account homepage | Working as expected | Pass |  |  |  | Chrissy Panfila V
LoginPage_TC_OO4 | Functional | Login page | Verify user is able to log into application with InValid credentials |  | 1.Enter URL and click go 2.Enter InValid username/email in Email text box 3.Enter valid password in password text box 4.Click on login button | Username: abc@gmail password: testuser-1 | Application should show 'Incorrect email or password ' validation message. | Working as expected | Pass |  |  |  | Sravya Sravani
LoginPage_TC_OO5 | Functional | Login page | Verify user is able to log into application with InValid credentials |  | 1.Enter URL and click go 2.Enter Valid username/email in Email text box 3.Enter Invalid password in password text box 4.Click on login button | Username: testuser@gmail.com password: test1234 | Application should show 'Incorrect email or password ' validation message. | Working as expected | Pass |  |  |  | Abbireddy Sai Jahnavi
LoginPage_TC_OO6 | Functional | Login page | Verify user is able to log into application with InValid credentials |  | 1.Enter URL and click go 2.Enter InValid username/email in Email text box 3.Enter Invalid password in password text box 4.Click on login button | Username: abc@gmail.com password: test1234 | Application should show 'Incorrect email or password ' validation message. | Working as expected | Pass |  |  |  | Chrissy Panfila V
LoginPage_TC_OO7 | Functional | Login Page | Check if signup link takes the user to the signup page |  | 1.Enter URL and click go 2. Click on the signup link |  | The signup page should be displayed | Working as expected | Pass |  |  |  | Anandhitha TR
LoginPage_TC_OO8 | UI | Signup page | Verify the UI elements in Signup page |  | 1.Enter URL and click go 2. Click on the signup link 3. Check if the following UI elements are present: a. Name textbox b. email textbox c. password textbox d. retype password textbox e. Beneficiary/Donor radio button f. Submit button g. Already a user? Login link |  | Application should show below UI elements: a. Name textbox b. email textbox c. password textbox d. retype password textbox e. Beneficiary/Donor radio button f. Submit button g. Already a user? Login link | Working as expected | Pass |  |  |  | Chrissy Panfila V
LoginPage_TC_OO9 | Functional | Signup page | Verify if the user is able to signup with invalid email |  | 1.Enter URL and click go 2. Click on the signup link 3. Enter an invalid email address 4. Fill other details 5. Click submit | name: Test User email: abc@gmail password: test1234 retype-password: test1234 | An error message stating the email is invalid should be displayed | Working as expected | Pass |  |  |  | Sravya Sravani
LoginPage_TC_O10 | Functional | Signup page | Verify if the user is able to signup with passwords that do not match |  | 1.Enter URL and click go 2. Click on the signup link 3. Type a password 4. Type a different password in retype-password field | name: Test User email: abc@gmail.com password: test1234 retype-password: test123456 | An error message stating the passwords do not match should be displayed | Working as expected | Pass |  |  |  | Anandhitha TR
LoginPage_TC_O11 | Functional | Signup page | Check if the users details are uploaded correctly in the database |  | 1.Enter URL and click go 2. Click on the signup link 3. Enter all required details 4. Click on submit | name: Test User email: abc@gmail.com password: test1234 retype-password: test1234 | The users signup details should be entered in the database | Working as expected | Pass |  |  |  | Sravya Sravani
LoginPage_TC_O12 | Functional | Signup page | After signup the user should be redirected to login page |  | 1.Enter URL and click go 2. Click on the signup link 3. Enter all required details 4. Click on submit |  | The user should be redirected to login page after signup | Working as expected | Pass |  |  |  | Abbireddy Sai Jahnavi
LoginPage_TC_O13 | Functional | Homepage | After login the user should be directed to home page |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. |  | The user should be directed to home page after login | Working as expected | Pass |  |  |  | Chrissy Panfila V
LoginPage_TC_O14 | UI | Homepage | Verify the UI elements in Home page |  | 1.Enter URL and click go 2. Login into the website 3. Check if the following UI elements are present: a.App name b. logout button c.Navigation bar |  | Application should show below UI elements: a.App name b. logout button c.Navigation bar | Working as expected | Pass |  |  |  | Abbireddy Sai Jahnavi
LoginPage_TC_O15 | Functional | Homepage | Check if the logout button logs the user out |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. 5. Click on logout button in homepage. |  | The user should be logged out of the applocation and redirected to login page | Working as expected | Pass |  |  |  | Sravya Sravani
LoginPage_TC_O16 | Functional | Dashboard | Check if navigation link to dashboard is working |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. 5. Click on dashboard in navbar |  | The dasboard should be displayed | Working as expected | Pass |  |  |  | Chrissy Panfila V
LoginPage_TC_O17 | Functional | Profile page | Check if navigation link to profile page is working |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. 5. Click on profile in navbar |  | The profile should be displayed | Working as expected | Pass |  |  |  | Anandhitha TR
LoginPage_TC_O18 | Functional | Contact page | Check if navigation link to contact page is working |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. 5. Click on contact in navbar |  | The contact page should be displayed | Working as expected | Pass |  |  |  | Sravya Sravani
LoginPage_TC_O19 | Functional | About page | Check if navigation link to about us page is working |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. 5. Click on about in navbar |  | The about page should be displayed | Working as expected | Pass |  |  |  | Chrissy Panfila V
LoginPage_TC_O20 | Functional | Profile page | Check if the password change is working with wrong password |  | 1.Go to profile page 2. Go to password tab 3.Enter wrong password in password field 4.Fill other details 5.Click on Submit button | Old password: test1234 New password: test-abcd Confirm password:test-abcd | The password should not change and display error message | Working as expected | Pass |  |  |  | Anandhitha TR
LoginPage_TC_O21 | Functional | Profile page | Check if the password change is working with correct credentials |  | 1.Go to profile page 2. Go to password tab 3.Enter old password in password field 4.Type new password and confirm 5.Click on Submit button | Old password: testuser-1 New password: test-abcd Confirm password:test-abcd | The password should be changed and updated in database | Working as expected | Pass |  |  |  | Abbireddy Sai Jahnavi
LoginPage_TC_O22 | Functional | Contact page | Check if the message entered in contact page is delivered correctly |  | 1.Enter URL and click go. 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on login button. 5. Click on contact in navbar | Hello I have a problem with contacting the donor | The message should be stored in database | Working as expected | Pass |  |  |  | Chrissy Panfila V

## Testscearnios
Test Scenarios
1 | Verify user is able to see login page
2 | Verify user is able to loginto application or not?
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to recovery password
5 | Veriify login page elements
Search
1 | Verify user is able to search by entering keywords in search box
2 | Verify user is able to see suggestions based on keyword entered in search box
3 | Verify user is able to see related auto suggestions displaying based on keyword entered in search box
4 | Verify user is able to see no matches found message when no results are matching with entered keyword
5 | Verify user is able to see seach detailed page when nothing entered in textbox